## Sheet1
|  |  | Estimated | Estimated | Estimated | Actual | Actual | Actual
Task ID | Task Name | Assigned To | Duration (days) | Start Date | Finish Data | Start Date 2 | Finish Data 2 | Duration Variance (days) | Dependency | Status
1 | Planning
1.1 | System Request | • Doaa Ahmed Gharib • Doaa Atef Muhammed | 36 | 2022-01-01 | 2022-02-06 | 2022-01-01 | 2022-01-10 | 9 |  | closed
1.2 | Feasibility
1.2.1 | Economic Feasibility | • Hussein Abd-Elkader • Enas Ragab | 36 | 2022-01-01 | 2022-02-06 | 2022-01-11 | 2022-01-20 | 9 |  | closed
1.2.2 | Technical Feasibility | • Doaa Othman • Salsabil Syed | 36 | 2022-01-01 | 2022-02-06 | 2022-01-21 | 2022-01-30 | 9 | 1.2.1 | closed
1.2.3 | Organization feasibility | • Doaa Atef Muhammed • Doaa Othman | 38 | 2022-02-07 | 2022-03-17 | 2022-02-07 | 2022-03-15 | 36 |  | closed
1.3 | Project work plan | • Hussein Abd-Elkader • Khaled Mohsen | 38 | 2022-02-07 | 2022-03-17 | 2022-02-10 | 2022-03-14 | 32 |  | closed
1.4 | Gannt chart | • Sanaa Mohamed • Salsabil Syed | 27 | 2022-03-18 | 2022-04-14 | 2022-03-18 | 2022-04-12 | 25 | 1.3 | closed
2 | Analysis
2.1 | Requirements
2.1.1 | Functional Requirements | • Hussein Abd-Elkader • Enas Ragab | 30 | 2022-04-15 | 2022-05-15 |  |  |  |  | open
2.1.2 | Nonfunctional Requirements | • Doaa Othman • Salsabil Syed | 30 | 2022-04-15 | 2022-05-15 |  |  |  |  | open
2.2 | Interviews
2.2.1 | Selecting Interviewees | • Hussein Abd-Elkader • Enas Ragab | 40 | 2022-05-16 | 2022-06-25 |  |  |  |  | open
2.2.2 | Designing Interview Questions | • Sanaa Mohamed • Salsabil Syed | 40 | 2022-05-16 | 2022-06-25 |  |  |  |  | open
2.2.3 | Preparing for the Interview | • Doaa Ahmed Gharib • Doaa Atef Muhammed | 40 | 2022-05-16 | 2022-06-25 |  |  |  |  | open
2.2.4 | Conducting the Interview | • Khaled Mohsen | 24 | 2022-06-26 | 2022-07-20 |  |  |  |  | open
2.2.5 | Post-interview Follow-up | • Hussein Abd-Elkader • Enas Ragab | 24 | 2022-06-26 | 2022-07-20 |  |  |  |  | open
2.3 | Root Cause Analysis | • Doaa Othman • Salsabil Syed | 24 | 2022-06-26 | 2022-07-20 |  |  |  |  | open
2.4 | Building Use Cases | • Doaa Ahmed Gharib • Doaa Othman | 20 | 2022-07-21 | 2022-08-10 |  |  |  |  | open
2.5 | Creating Data Flow Diagram | • Khaled Mohsen | 20 | 2022-07-21 | 2022-08-10 |  |  |  |  | open
2.6 | Creating ERD | • Sanaa Mohamed • Salsabil Syed | 20 | 2022-07-21 | 2022-08-10 |  |  |  |  | open
3 | Design
3.1 | creating Alternative Matrix | • Khaled Mohsen | 35 | 2022-08-11 | 2022-09-15 |  |  |  |  | open
3.2 | Design Requirements | • Hussein Abd-Elkader • Enas Ragab | 35 | 2022-08-11 | 2022-09-15 |  |  |  |  | open
3.2.1 | Operational Requirements | • Doaa Othman • Salsabil Syed | 35 | 2022-08-11 | 2022-09-15 |  |  |  |  | open
3.2.2 | Performance Requirements | • Doaa Ahmed Gharib • Doaa Othman | 35 | 2022-09-16 | 2022-10-21 |  |  |  |  | open
3.2.3 | Security Requirements | • Hussein Abd-Elkader • Enas Ragab | 35 | 2022-09-16 | 2022-10-21 |  |  |  |  | open
3.2.4 | Cultural and Political Requirements | • Sanaa Mohamed • Salsabil Syed | 35 | 2022-09-16 | 2022-10-21 |  |  |  |  | open
3.3 | Tune Source ISD | • Khaled Mohsen | 35 | 2022-10-22 | 2022-11-26 |  |  |  |  | open
3.4 | Program Design |  | 35 | 2022-10-22 | 2022-11-26 |  |  |  |  | open
3.5 | Data Storage Design | • Hussein Abd-Elkader • Enas Ragab | 35 | 2022-10-22 | 2022-11-26 |  |  |  |  | open
4 | Implementation
4.1 | Android app | • Doaa Ahmed Gharib • Doaa Othman | 33 | 2022-11-27 | 2022-12-30 |  |  |  |  | open
4.2 | IOS app | • Hussein Abd-Elkader • Enas Ragab | 33 | 2022-11-27 | 2022-12-30 |  |  |  |  | open
4.3 | Website | • Sanaa Mohamed • Salsabil Syed | 33 | 2022-11-27 | 2022-12-30 |  |  |  |  | open
4.4 | Test Plan | • Khaled Mohsen | 33 | 2022-11-27 | 2022-12-30 |  |  |  |  | open
4.5 | Documentation | • Doaa Ahmed Gharib • Doaa Othman | 33 | 2022-11-27 | 2022-12-30 |  |  |  |  | open
4.6 | Problem Reports | • Hussein Abd-Elkader • Enas Ragab | 33 | 2022-11-27 | 2022-12-30 |  |  |  |  | open
4.7 | Project Assessment | • Khaled Mohsen | 33 | 2022-11-27 | 2022-12-30 |  |  |  |  | open